## Sheet1
DETAILS OF WORKS AWARDED (WORKSHOP AREA & COLONY AREA)
S.N | Tender No. | Item / Nature of work | Mode of Tender Enquiry | Date of Publication of NIT | Type of Bidding (Single / Two Bid System) | Last date of receipt of tender | Nos. of tenders recd. | Nos. & names of parties qualified after technical evaluation. | Nos. & names of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer / Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract/ Original | Scheduled date of completion of supplies | Actual date of start of work | Actual date of complete | Reasons for delays if any
1 | CE/PLW/T-10/2022-23/PTA | Providing CC interlocking tile and CC flooring in scrap yard, workshop area, PLW/Patiala. 2022-23 | Internet/ Manual | - | NA | 18.08.2022 | - | NA | NA | Yes | CE/PLW/T-10/2022-23/PTA | M/s Galaxy Floor Pvt. Ltd., Uttrakhand | 2039999/- | 12.03.2023 | 13.10.2022 | 28.02.2023 | Work Completed
2 | CE/PLW/T-12/2022-23/PTA | Re-construction & Re-levelling of track in LAS pits in workshop area, PLW/Patiala. (2022-23) | Internet/ Manual | - | NA | 18.08.2022 | - | NA | NA | Yes | CE/PLW/T-12/2022-23/PTA | M/s Anjana Enterprises, Patiala. | 2100749/- | 21.01.2023 | 01.10.2022 | 20.02.2023 | Work Completed
3 | CE/PLW/T-14/2022-23/PTA | Solid waste management services including door to door collec tion and its environment friendly disposal viz. Conversion into compost etc. & collectioin of waste from dustbing of colony No. I & II (For two years), PLW premises, Patiala. | Internet/ Manual | - | NA | 21.01.2023 | - | NA | NA | Yes | CE/PLW/T-14/2022-23/PTA | M/s Hari Bhari, Patiala. | 5150000/- | 15.02.2025 | 16.02.2023 | - | Work in Progress
4 | CE/PLW/T-15/2022-23/PTA | Repairing of boundary wall with barbed wire concertina wire in back side of hospital (from KV-II to SBI bank) in Col-II area PLW, Patiala. (2022-23) | Internet/ Manual | - | NA | 27.09.2022 | - | NA | NA | Yes | CE/PLW/T-15/2022-23/PTA | M/s Kanwaljeet Singh, Patiala | 706817/- | 26.03.2023 | 27.10.2022 | 14.02.2023 | Work in Progress
5 | CE/PLW/T-16/2022-23/PTA | De-silting & cleaning of sewer line through sewer suction machine in col-I & II area in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-16/2022-23/PTA | M/s RAI Constructios, Jalandhar | 2020849/- | 01.01.2024 | 02.01.2023 | - | Work in Progress
6 | CE/PLW/T-18/2022-23/PTA | Colour washing (inside & outside) in various shops in workshop area (PH-I), PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 18.10.2022 | - | NA | NA | Yes | CE/PLW/T-18/2022-23/PTA | S.K Builders, Patiala | 1491990/- | 30.03.2023 | 14.11.2022 | - | Work in Progress
7 | CE/PLW/T-19/2022-23/PTA | Development & Maintenance of Horticulture works in col-I, II, W/shop & Admn. Bldg. Area PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 21.10.2022 | - | NA | NA | Yes | CE/PLW/T-19/2022-23/PTA | M/s Modern Const. Co., Patiala. | 9884449/- | 30.10.2023 | 01.11.2022 | - | Work in Progress
8 | CE/PLW/T-20/2022-23/PTA | Repair to roads in colony-II in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-20/2022-23/PTA | M/s Krishan Kumar, Patiala. | 8558277/- | 15.05.2023 | 16.11.2022 | - | Work in Progress
9 | CE/PLW/T-22/2022-23/PTA | Roof covering in '0' BAY in LMS (16m x 20m) in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 29.11.2022 | - | NA | NA | Yes | CE/PLW/T-22/2022-23/PTA | M/s Gufraan Contractor and General order supplier, U.P | 1641754/- | 05.06.2023 | 20.01.2023 | - | Work in Progress
10 | CE/PLW/T-24/2022-23/PTA | Providing & Laying interlocking tiles from HMS level X-ing to bogie shop including footpath, rear side of LRS & LPG tank to PPS in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 30.11.2022 | - | NA | NA | Yes | CE/PLW/T-24/2022-23/PTA | M/s S.K Builders, Patiala. | 5594445/- | 25.06.2023 | 02.01.2023 | - | Work in Progress
11 | CE/PLW/T-27/2022-23/PTA | Providing & Fixing of wooden flooring in badminton court in staff institution colony-II, PLW, Patiala. (2022-23) | Internet/ Manual | - | NA | 14.02.2023 | - | NA | NA | Yes | CE/PLW/T-27/2022-23/PTA | M/s Parquet Sports, Faridabad, India. | 879024/- | 15.07.2023 | 16.03.2023 | - | Work in Progress
12 | CE/PLW/T-29/2022-23/PTA | Operation, Repair and Maintenance of Sewage Treatment Plant in colony-II, PLW/Patiala for two years 2023-24 & 2024-25 | Internet/ Manual | - | NA | 22.03.2023 | - | NA | NA | Yes | CE/PLW/T-29/2022-23/PTA | M/s CHEM ECO Engineers | 2494800/- | 20.04.2023 | 19.04.2025 | - | Work in Progress

## Sheet 2
DETAILS OF WORKS AWARDED (WORKSHOP AREA & COLONY AREA)
S.N | Tender No. | Item / Nature of work | Mode of Tender Enquiry | Date of Publication of NIT | Type of Bidding (Single / Two Bid System) | Last date of receipt of tender | Nos. of tenders recd. | Nos. & names of parties qualified after technical evaluation. | Nos. & names of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer / Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract/ Original | Scheduled date of completion as per CA | Actual date of start of work | Actual date of complete/extended | Reasons for delays if any
1 | CE/PLW/T-14/2023-24/PTA | Covering of roof (68m x 20m) and flooring of steel yard adjoining bogie shop for upgradation/augmentation of electric & diesel locomotive maintenance & production facilities of PLW/Patiala. (2023-24) | Internet/ Manual | - | NA | 22.08.2023 | - | NA | NA | Yes | CE/PLW/T-14/2023-24/PTA | M/s S.K Builders, Patiala. | 22311840/- | 10.05.2024 | 25.09.2023 | 10.05.2024 | Work In Progress
2 | CE/PLW/T-15/2023-24/PTA | Filling and levelling of lagoon by earth filling near CETP in workshop area, PLW/Patiala. (2023-24) | Internet/ Manual | - | NA | 25.08.2023 | - | NA | NA | Yes | CE/PLW/T-15/2023-24/PTA | M/s PAL Enterprises, Patiala. | 377505/- | 03.11.2023 | 05.09.2023 | 21.10.2023 | Work Completed
3 | CE/PLW/T-17/2023-24/PTA | Dismentle/Demolish of three No’s RCC Over Head Water Tanks of 450 KL Capacity (Near Hospital, Near SSE/Electrical Office & Workshop) and having staging height 25 to 30 meter along with adjacent steel stair case in colony-II & workshop area of PLW, Patiala. (Contractor will pay to Railway) | Internet/ Manual | - | NA | 26.10.2023 | - | NA | NA | Yes | CE/PLW/T-17/2023-24/PTA | M/s MOHD. AHSON INFRA PVT. LTD. | 3430671/- | 12.08.2024 | - | - | Yet to be started
4 | CE/PLW/T-18/2023-24/PTA | Covering of HMS &TMS Level Crossing on Front Side (18m x 60m), repair of damaged floor by providing Hardonite Flooring, Construction of two nos. inspection Pits and Dismantling of Platform Between TMS-HMS level crossing and laying of strom water line along with other allied works in workshop area, PLW Patiala. | Internet/ Manual | - | NA | 18.11.2023 | - | NA | NA | Yes | CE/PLW/T-18/2023-24/PTA | M/s S.K Builders, Patiala. | 20599436/- | 24.04.2024 | 01.12.2023 | 15.06.2024 | Work In Progress
5 | CE/PLW/T-21/2023-24/PTA | Tree Plantation in PLW complex Patiala for the year 2023-24 (1750 trees with two months maintenance) | Internet/ Manual | - | NA | 05.12.2023 | - | NA | NA | Yes | CE/PLW/T-21/2023-24/PTA | M/s Moder Const. Co., Patiala. | 424048/- | 02.05.2024 | 18.01.2024 | 02.05.2024 | Work In Progress
6 | CE/PLW/T-23/2023-24/PTA | Repair & strengthening of workshop boundary including increase in height of boundary wall from scrap yard to RPF barrack in workshop area, PLW/Patiala. | Internet/ Manual | - | NA | 21.12.2023 | - | NA | NA | Yes | CE/PLW/T-23/2023-24/PTA | M/s RR Builders, Ludhiana | 6727779/- | 11.08.2024 | 27.01.2024 | 11.08.2024 | Work In Progress
7 | CE/PLW/T-24/2023-24/PTA | Renovation of sports facilities in colony-I, extension of false ceiling of modern gym hall in stadium area and other allied works in PLW Patiala. | Internet/ Manual | - | NA | 21.12.2023 | - | NA | NA | Yes | CE/PLW/T-24/2023-24/PTA | M/s Moder Const. Co., Patiala. | 794129/- | 02.07.2024 | 02.02.2024 (LOA DATE) | - | Work In Progress
8 | CE/PLW/T-26/2023-24/PTA | Repair and Upgradation of bath and toilets in staff rest house in colony-II area, PLW/Patiala. (2023-24) | Internet/ Manual | - | NA | 23.12.2023 | - | NA | NA | Yes | CE/PLW/T-26/2023-24/PTA | M/s PAL Enterprises, Patiala. | 1669565/- | 17.06.2024 | 24.01.2024 | - | Work In Progress
9 | CE/PLW/T-27/2023-24/PTA | Replacement of damaged pipeline in workshop area PLW, Patiala. | Internet/ Manual | - | NA | 23.12.2023 | - | NA | NA | Yes | CE/PLW/T-27/2023-24/PTA | M/s Balraj Singh Contractor, Patiala | 1151851/- | 01.06.2024 | - | 01.06.2024 | Work In Progress
10 | CE/PLW/T-28/2023-24/PTA | Augmentation of drainage system to collect rain water/storm sewer in pit (Phase-II) workshop area PLW/Patiala. | Internet/ Manual | - | NA | 08.01.2024 | - | NA | NA | Yes | CE/PLW/T-28/2023-24/PTA | M/s Balraj Singh Contractor, Patiala | 4158548/- | 17.07.2024 | 05.02.2024 | 17.07.2024 | Work In Progress
11 | CE/PLW/T-29/2023-24/PTA | Providing and Fixing MS steel cupboard shutters in Type-II, III & IV qtrs. In colony-II, PLW/Patiala. (2023-24) | Internet/ Manual | - | NA | 09.01.2024 | - | NA | NA | Yes | CE/PLW/T-29/2023-24/PTA | M/s GS Builder, Kapurthala | 15816260/- | 02.10.2024 | 03.02.2024 (LOA DATE) | - | Yet to be started
12 | CE/PLW/T-31/2023-24/PTA | Repair to damaged plastering and strengthening of boundary wall in Colony-I, Colony-II & Golf/Stadium area PLW/ Paiala for this year 2023-24 | Internet/ Manual | - | NA | 26.02.2024 | - | NA | NA | Yes | CE/PLW/T-31/2023-24/PTA | M/s Galaxy floor Pvt. Ltd., Uttrakhand | 9887887/- | 12.11.2024 | - | - | Yet to be started
13 | CE/PLW/T-34/2023-24/PTA | Repair to old damaged RCC mumties by GC sheets in Type-II (90 stair cases), Type-III (38 stair cases), Type-IV (2 stair cases) quarters in colony-2 PLW, Patiala. (2023-24) | Internet/ Manual | - | NA | 27.01.2024 | - | NA | NA | Yes | CE/PLW/T-34/2023-24/PTA | M/s Gupta Const. Co., Bathinda | 6641361/- | 31.10.2024 | 01.03.2024 (LOA DATE) | - | Work In Progress
14 | CE/PLW/T-35/2023-24/PTA | Repair to damaged balconies chajja, plaster and other allied works of Type-II & III quarters in colony-II, PLW, Patiala. (2023-24) | Internet/ Manual | - | NA | 30.01.2024 | - | NA | NA | Yes | CE/PLW/T-35/2023-24/PTA | M/s Balraj Singh Contractor, Patiala | 6120836/- | 30.09.2024 | 01.03.2024 (LOA DATE) | - | Work In Progress
15 | CE/PLW/T-36/2023-24/PTA | Improvement and Rectification with mechanical equipment and civil works of swimming pool in Colony-II area and Operation, Cleaning and Maintenance of swimming pool in Colony-II of PLW/PTA | Internet/ Manual | - | NA | 28.02.2024 | - | NA | NA | Yes | CE/PLW/T-36/2023-24/PTA | M/s NEXUS Marketing, Sangrur | 1980353/- | 12.08.2024 | - | - | Yet to be started
16 | CE/PLW/T-41/2023-24/PTA | Colour washing (inside and outside) in HMS, MRS, TMS, DETC WARD near HMS & Scrap Yard & replacing damaged glass and damaged louvers with poly carbonate sheets in HMS, MRS, TMS, DETC WARD near HMS & Scrap Yard, LAS, LFS, BOGIE SHOP, PPS, PAINT SHOP, LTS in Workshop area, PLW/PTA (2023-24) | Internet/ Manual | - | NA | 06.03.2024 | - | NA | NA | Yes | CE/PLW/T-41/2023-24/PTA | M/s GOBIND GUPTA- JIND, HARYANA | 15558323/- | 23.12.2024 | - | 23.12.2024 | Work In Progress
17 | CE/PLW/T-42/2023-24/PTA | Construction of Drug strore & toilets in PLW Hospital in colony-II, PLW, Patiala. | Internet/ Manual | - | NA | 12.03.2024 | - | NA | NA | Yes | CE/PLW/T-42/2023-24/PTA | M/s Kanwaljeet Singh, Govt. Contractor-Patiala. | 2940539/- | 31.10.2024 | 01.05.2024 (LOA DATE) | - | Yet to be started
18 | CE/PLW/T-43/2023-24/PTA | Renovation of Camp office and Construction of septic tank & soak pit in camp office, Tilak Bridge New Delhi, PLW/Patiala. | Internet/ Manual | - | NA | 12.03.2024 | - | NA | NA | Yes | CE/PLW/T-43/2023-24/PTA | M/s ZEMENT INFRATECH PVT. LTD., BENGALURU | 1926201/- | 23.12.2024 | - | - | Yet to be started
19 | CE/PLW/T-44/2023-24/PTA | Repair of roof leakage in Type-IV special & Type-V quarters in colony-I area (Type-IV special- 27 Nos., Type-V 44 Nos.) and Type-II, Type-III quarters & Type-IV quarters in colony-II area (Type-II-90 Nos., Type-III-30 Nos., Type-IV-30 Nos.), in colony-II area PLW/Patiala. | Internet/ Manual | - | NA | 13.03.2024 | - | NA | NA | Yes | CE/PLW/T-43/2023-24/PTA | M/s SATYAN Kumar Govt. Contractor, Samana, Patiala. | 15827484/- | 23.01.2025 | - | - | Yet to be started
18 | CE/PLW/T-45/2023-24/PTA | Providing and fixing of Jali doors in balance type-II qtrs. (293) of colony-II, PLW/Patiala. | Internet/ Manual | - | NA | 14.03.2024 | - | NA | NA | Yes | CE/PLW/T-45/2023-24/PTA | M/s S.K VIG, DELHI | 7143680/- | 23.10.2024 | - | - | Yet to be started
18 | CE/PLW/T-47/2023-24/PTA | Water proofing treatment to damaged roof units of different shops of Phase-II area (LAS, Bogie Shop, LFS, PPS, Paint Shop, LTS) in workshop area, PLW/Patiala. | Internet/ Manual | - | NA | 26.03.2024 | - | NA | NA | Yes | CE/PLW/T-47/2023-24/PTA | M/s S.K Builders, Patiala. | 5791437/- | 24.10.2024 | - | 24.10.2024 | Yet to be started
18 | CE/PLW/T-49/2023-24/PTA | Housekeeping and maintenance of Camp Office at Tilak Bridge New Delhi (For twenty four months) PLW/PTA. | Internet/ Manual | - | NA | 25.05.2024 | - | NA | NA | Yes | CE/PLW/T-49/2023-24/PTA | M/s DIVINE ESTATE PLANNERS & HOPITALITY, PATIALA | 3170757/- | 01.05.2026 | 02.05.2024 (LOA DATE) | 01.05.2026 | Yet to be started
18 | CE/PLW/T-50/2023-24/PTA | Housekeeping and maintenance of officer Rest House in Colony-I and staff Rest House in Colony- 2 (For 24 months) PLW/PTA. | Internet/ Manual | - | NA | 25.05.2024 | - | NA | NA | Yes | CE/PLW/T-50/2023-24/PTA | M/s Kanwaljeet Singh, Govt. Contractor-Patiala. | 4232056/- | 01.05.2026 | 02.05.2024 (LOA DATE) | 01.05.2026 | Yet to be started