## Sheet1
DETAILS OF WORKS AWARDED (WORKSHOP AREA & COLONY AREA)
S.N | Tender No. | Item / Nature of work | Mode of Tender Enquiry | Date of Publication of NIT | Type of Bidding (Single / Two Bid System) | Last date of receipt of tender | Nos. of tenders recd. | Nos. & names of parties qualified after technical evaluation. | Nos. & names of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer / Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract/ Original | Scheduled date of completion of supplies | Actual date of start of work | Actual date of complete | Reasons for delays if any
1 | CE/PLW/T-10/2022-23/PTA | Providing CC interlocking tile and CC flooring in scrap yard, workshop area, PLW/Patiala. 2022-23 | Internet/ Manual | - | NA | 18.08.2022 | - | NA | NA | Yes | CE/PLW/T-10/2022-23/PTA | M/s Galaxy Floor Pvt. Ltd., Uttrakhand | 2039999/- | 12.03.2023 | 13.10.2022 | 28.02.2023 | Work Completed
2 | CE/PLW/T-12/2022-23/PTA | Re-construction & Re-levelling of track in LAS pits in workshop area, PLW/Patiala. (2022-23) | Internet/ Manual | - | NA | 18.08.2022 | - | NA | NA | Yes | CE/PLW/T-12/2022-23/PTA | M/s Anjana Enterprises, Patiala. | 2100749/- | 21.01.2023 | 01.10.2022 | 20.02.2023 | Work Completed
3 | CE/PLW/T-14/2022-23/PTA | Solid waste management services including door to door collec tion and its environment friendly disposal viz. Conversion into compost etc. & collectioin of waste from dustbing of colony No. I & II (For two years), PLW premises, Patiala. | Internet/ Manual | - | NA | 21.01.2023 | - | NA | NA | Yes | CE/PLW/T-14/2022-23/PTA | M/s Hari Bhari, Patiala. | 5150000/- | 15.02.2025 | 16.02.2023 | - | Work in Progress
4 | CE/PLW/T-15/2022-23/PTA | Repairing of boundary wall with barbed wire concertina wire in back side of hospital (from KV-II to SBI bank) in Col-II area PLW, Patiala. (2022-23) | Internet/ Manual | - | NA | 27.09.2022 | - | NA | NA | Yes | CE/PLW/T-15/2022-23/PTA | M/s Kanwaljeet Singh, Patiala | 706817/- | 26.03.2023 | 27.10.2022 | 14.02.2023 | Work in Progress
5 | CE/PLW/T-16/2022-23/PTA | De-silting & cleaning of sewer line through sewer suction machine in col-I & II area in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-16/2022-23/PTA | M/s RAI Constructios, Jalandhar | 2020849/- | 01.01.2024 | 02.01.2023 | - | Work in Progress
6 | CE/PLW/T-18/2022-23/PTA | Colour washing (inside & outside) in various shops in workshop area (PH-I), PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 18.10.2022 | - | NA | NA | Yes | CE/PLW/T-18/2022-23/PTA | S.K Builders, Patiala | 1491990/- | 30.03.2023 | 14.11.2022 | - | Work in Progress
7 | CE/PLW/T-19/2022-23/PTA | Development & Maintenance of Horticulture works in col-I, II, W/shop & Admn. Bldg. Area PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 21.10.2022 | - | NA | NA | Yes | CE/PLW/T-19/2022-23/PTA | M/s Modern Const. Co., Patiala. | 9884449/- | 30.10.2023 | 01.11.2022 | - | Work in Progress
8 | CE/PLW/T-20/2022-23/PTA | Repair to roads in colony-II in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-20/2022-23/PTA | M/s Krishan Kumar, Patiala. | 8558277/- | 15.05.2023 | 16.11.2022 | - | Work in Progress
9 | CE/PLW/T-22/2022-23/PTA | Roof covering in '0' BAY in LMS (16m x 20m) in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 29.11.2022 | - | NA | NA | Yes | CE/PLW/T-22/2022-23/PTA | M/s Gufraan Contractor and General order supplier, U.P | 1641754/- | 05.06.2023 | 20.01.2023 | - | Work in Progress
10 | CE/PLW/T-24/2022-23/PTA | Providing & Laying interlocking tiles from HMS level X-ing to bogie shop including footpath, rear side of LRS & LPG tank to PPS in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 30.11.2022 | - | NA | NA | Yes | CE/PLW/T-24/2022-23/PTA | M/s S.K Builders, Patiala. | 5594445/- | 25.06.2023 | 02.01.2023 | - | Work in Progress
11 | CE/PLW/T-27/2022-23/PTA | Providing & Fixing of wooden flooring in badminton court in staff institution colony-II, PLW, Patiala. (2022-23) | Internet/ Manual | - | NA | 14.02.2023 | - | NA | NA | Yes | CE/PLW/T-27/2022-23/PTA | M/s Parquet Sports, Faridabad, India. | 879024/- | 15.07.2023 | 16.03.2023 | - | Work in Progress
12 | CE/PLW/T-29/2022-23/PTA | Operation, Repair and Maintenance of Sewage Treatment Plant in colony-II, PLW/Patiala for two years 2023-24 & 2024-25 | Internet/ Manual | - | NA | 22.03.2023 | - | NA | NA | Yes | CE/PLW/T-29/2022-23/PTA | M/s CHEM ECO Engineers | 2494800/- | 20.04.2023 | 19.04.2025 | - | Work in Progress

## Sheet 2
DETAILS OF WORKS AWARDED (WORKSHOP AREA & COLONY AREA)
S.N | Tender No. | Item / Nature of work | Mode of Tender Enquiry | Date of Publication of NIT | Type of Bidding (Single / Two Bid System) | Last date of receipt of tender | Nos. of tenders recd. | Nos. & names of parties qualified after technical evaluation. | Nos. & names of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer / Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract/ Original | Scheduled date of completion of supplies | Actual date of start of work | Actual date of complete | Reasons for delays if any
1 | CE/PLW/T-16/2022-23/PTA | Desilting & cleaning of sewer line through sewer suction machine3 in col-I & II area in PLW/PTA | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-16/2022-23/PTA | M/s RAI Constructios, Jalandhar | 2020849/- | 16.02.2023 | 02.01.2023 | - | Work Completed
2 | CE/PLW/T-18/2022-23/PTA | Colour washing (inside and outside) in various shops in workshop area (PH-I), PLW Patiala. (2022-23) | Internet/ Manual | - | NA | 18.10.2022 | - | NA | NA | Yes | CE/PLW/T-18/2022-23/PTA | M/s S.K Builders, Patiala. | 1491990/- | 30.04.2023 | 14.11.2022 | 15.06.2023 | Work Completed
3 | CE/PLW/T-19/2022-23/PTA | Development & Maintenance of horticulture works in colony I, II, Workshop & Admin. Building area PLW/Patiala for the year. (2022-23) | Internet/ Manual | - | NA | 21.10.2022 | - | NA | NA | Yes | CE/PLW/T-19/2022-23/PTA | M/s Modern Const. Co., Patiala. | 9884449/- | 30.10.2023 | 01.11.2022 | - | Work in Progress
4 | CE/PLW/T-20/2022-23/PTA | Repair to roads in colony-II in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-20/2022-23/PTA | M/s Krishan Kumar, Patiala. | 8558277/- | 30.06.2023 | 17.01.2023 | - | Work Completed
5 | CE/PLW/T-22/2022-23/PTA | Roof covering in '0' BAY in LMS (16m x 20m) in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 29.11.2022 | - | NA | NA | Yes | CE/PLW/T-22/2022-23/PTA | M/s Gufraan Contractor and General order supplier, U.P | 1641754/- | 05.06.2023 | 20.01.2023 | 20.06.2023 | Work Completed
6 | CE/PLW/T-24/2022-23/PTA | Providing & Laying interlocking tiles from HMS level X-ing to bogie shop including foot path, rear side of LRS & LPG tank to PPS In workshop area, PLW, Patiala.(2022-23) | Internet/ Manual | - | NA | 30.11.2022 | - | NA | NA | Yes | CE/PLW/T-24/2022-23/PTA | S.K Builders, Patiala | 5594445/- | 25.06.2023 | 02.01.2023 | 30.04.2023 | Work Completed
7 | CE/PLW/T-25/2022-23/PTA | Toilets cleaning and road sweeping service in workshop area, PLW/ Patiala (For two years) 2022-24 | Internet/ Manual | - | NA | 24.01.2023 | - | NA | NA | Yes | CE/PLW/T-25/2022-23/PTA | M.K Enterprises, U.P | 4424250/- | 30.06.2025 | 13.07.2023 | - | Work in Progress
8 | CE/PLW/T-26/2022-23/PTA | Water Proofing treatment of flat roof in Workshop area and Administrative Building PLW, Patiala. | Internet/ Manual | - | NA | 14.02.2023 | - | NA | NA | Yes | CE/PLW/T-26/2022-23/PTA | M/s Pratham const. co., Ferozepur. | 3999120/- | 30.10.2023 | 01.03.2023 (LOA Date) | - | Work in Progress
9 | CE/PLW/T-27/2022-23/PTA | Providing & Fixing of wooden flooring in badminton court in staff institution Colony-II PLW/Patiala. (2022-23) | Internet/ Manual | - | NA | 14.02.2023 | - | NA | NA | Yes | CE/PLW/T-27/2022-23/PTA | M/s Parquet Sports, Faridabad, India. | 879024/- | 15.08.2023 | 16.03.2023 | - | Work Completed
10 | CE/PLW/T-29/2022-23/PTA | Operation, Repair and Maintenance of Sewage Treatment Plant in Colony-II, PLW/Patiala, for two years for the year 2023-24 & 2024-25. | Internet/ Manual | - | NA | 22.03.2023 | - | NA | NA | Yes | CE/PLW/T-29/2022-23/PTA | M/s CHEM ECO Engineers | 2494800/- | 19.04.2025 | 22.04.2023 | - | Work in Progress
11 | CE/PLW/T-32/2022-23/PTA | Balance work for providing and fixing vitrifies tile in balance rooms & toilets of Type-IV quarters in Colony-I, PLW, Patiala. | Internet/ Manual | - | NA | 28.04.2023 | - | NA | NA | Yes | CE/PLW/T-32/2022-23/PTA | M/s Gandhi Builders, kapurthala | 2753475/- | 16.01.2024 | 10.05.2023 | - | Work in Progress
12 | CE/PLW/T-01/2023-24/PTA | Annual Maintenance of Gantry Girders and Track of EOT/Cranes of various shops for one year in workshop area PLW/Patiala. (2023-24) | Internet/ Manual | - | NA | 26.05.2023 | - | NA | NA | Yes | CE/PLW/T-01/2023-24/PTA | A.K Builders, Kapurthala | 2467974/- | 20.06.2024 | 21.06.2023 (LOA Date) | - | Work in Progress
13 | CE/PLW/T-02/2023-24/PTA | Annual Maintenance of electronic dosing pumps for water chlorination (For two years) at PLW/Patiala. 2023-25 | Internet/ Manual | - | NA | 14.07.2023 | - | NA | NA | Yes | CE/PLW/T-02/2023-24/PTA | Divine, Patiala. | 269199/- | 30.07.2025 | 22.07.2023 (LOA Date) | - | Work in Progress
14 | CE/PLW/T-07/2023-24/PTA | Repair and maintenance of assets of Zone work for Colony-I Qtrs, Site office, all Service Buildings of col-1 and service building as KV-II,Bank, Hospital, Postoffice, Auditorium, Staff Institute of col-II area including Camp office New Delhi, PLW Patiala (2023-24) | Internet/ Manual | - | NA | 14.07.2023 | - | NA | NA | Yes | CE/PLW/T-07/2023-24/PTA | M/s Sarwan Kumar & Co., Fazilka | 14924988/- | 30.06.2024 | 28.07.2023 (LOA Date) | - | Work in Progress
15 | CE/PLW/T-08/2023-24/PTA | Repair and Maintenance of Assets in Admn. Building & Workshop area, PLW/Patiala zone work for the year. 2023-24 | Internet/ Manual | - | NA | 19.07.2023 | - | NA | NA | Yes | CE/PLW/T-08/2023-24/PTA | M/s Akash Builders, Delhi | 12176012/- | 30.06.2024 | 07.08.2023 (LOA Date) | - | Work in Progress
16 | CE/PLW/T-09/2023-24/PTA | Annual Maintenance of P-Way siding in workshop area PLW, Patiala. | Internet/ Manual | - | NA | 26.05.2023 | - | NA | NA | Yes | CE/PLW/T-09/2023-24/PTA | Gandhi Builders, Kapurthala | 2433311/- | 02.08.2024 | 03.08.2023 (LOA Date) | - | Work in Progress
17 | CE/PLW/T-10/2023-24/PTA | Zone work for Maintenance and Upkeep of all internal & external assets of Type- I, II, III & IV qtrs. including stair cases and service building in colony-II area, PLW/PTA. 2023-24 | Internet/ Manual | - | NA | 28.07.2023 | - | NA | NA | Yes | CE/PLW/T-10/2023-24/PTA | M/s S.K. VIG, E-32, Vijay Laxmi 98 IP Extn., Delhi | 35508146/- | 30.06.2024 | 16.08.2023 (LOA Date) | - | Work in Progress
18 | CE/PLW/T-11/2023-24/PTA | Provision of new footings and columns for gantry support in Bogie shop in workshop area, PLW/Patiala. 2023-24 | Internet/ Manual | - | NA | 09.08.2023 | - | NA | NA | Yes | CE/PLW/T-11/2023-24/PTA | M/s S.K Builders, Patiala. | 18095692/- | 17.02.2024 | 18.08.2023 (LOA Date) | - | Work in Progress