## Sheet1
DETAILS OF WORKS AWARDED (WORKSHOP AREA & COLONY AREA)
S.N | Tender No. | Item / Nature of work | Mode of Tender Enquiry | Date of Publication of NIT | Type of Bidding (Single / Two Bid System) | Last date of receipt of tender | Nos. of tenders recd. | Nos. & names of parties qualified after technical evaluation. | Nos. & names of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer / Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract/ Original | Scheduled date of completion of supplies | Actual date of start of work | Actual date of complete | Reasons for delays if any
1 | CE/PLW/T-10/2022-23/PTA | Providing CC interlocking tile and CC flooring in scrap yard, workshop area, PLW/Patiala. 2022-23 | Internet/ Manual | - | NA | 18.08.2022 | - | NA | NA | Yes | CE/PLW/T-10/2022-23/PTA | M/s Galaxy Floor Pvt. Ltd., Uttrakhand | 2039999/- | 12.03.2023 | 13.10.2022 | 28.02.2023 | Work Completed
2 | CE/PLW/T-12/2022-23/PTA | Re-construction & Re-levelling of track in LAS pits in workshop area, PLW/Patiala. (2022-23) | Internet/ Manual | - | NA | 18.08.2022 | - | NA | NA | Yes | CE/PLW/T-12/2022-23/PTA | M/s Anjana Enterprises, Patiala. | 2100749/- | 21.01.2023 | 01.10.2022 | 20.02.2023 | Work Completed
3 | CE/PLW/T-14/2022-23/PTA | Solid waste management services including door to door collec tion and its environment friendly disposal viz. Conversion into compost etc. & collectioin of waste from dustbing of colony No. I & II (For two years), PLW premises, Patiala. | Internet/ Manual | - | NA | 21.01.2023 | - | NA | NA | Yes | CE/PLW/T-14/2022-23/PTA | M/s Hari Bhari, Patiala. | 5150000/- | 15.02.2025 | 16.02.2023 | - | Work in Progress
4 | CE/PLW/T-15/2022-23/PTA | Repairing of boundary wall with barbed wire concertina wire in back side of hospital (from KV-II to SBI bank) in Col-II area PLW, Patiala. (2022-23) | Internet/ Manual | - | NA | 27.09.2022 | - | NA | NA | Yes | CE/PLW/T-15/2022-23/PTA | M/s Kanwaljeet Singh, Patiala | 706817/- | 26.03.2023 | 27.10.2022 | 14.02.2023 | Work in Progress
5 | CE/PLW/T-16/2022-23/PTA | De-silting & cleaning of sewer line through sewer suction machine in col-I & II area in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-16/2022-23/PTA | M/s RAI Constructios, Jalandhar | 2020849/- | 01.01.2024 | 02.01.2023 | - | Work in Progress
6 | CE/PLW/T-18/2022-23/PTA | Colour washing (inside & outside) in various shops in workshop area (PH-I), PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 18.10.2022 | - | NA | NA | Yes | CE/PLW/T-18/2022-23/PTA | S.K Builders, Patiala | 1491990/- | 30.03.2023 | 14.11.2022 | - | Work in Progress
7 | CE/PLW/T-19/2022-23/PTA | Development & Maintenance of Horticulture works in col-I, II, W/shop & Admn. Bldg. Area PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 21.10.2022 | - | NA | NA | Yes | CE/PLW/T-19/2022-23/PTA | M/s Modern Const. Co., Patiala. | 9884449/- | 30.10.2023 | 01.11.2022 | - | Work in Progress
8 | CE/PLW/T-20/2022-23/PTA | Repair to roads in colony-II in PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 31.10.2022 | - | NA | NA | Yes | CE/PLW/T-20/2022-23/PTA | M/s Krishan Kumar, Patiala. | 8558277/- | 15.05.2023 | 16.11.2022 | - | Work in Progress
9 | CE/PLW/T-22/2022-23/PTA | Roof covering in '0' BAY in LMS (16m x 20m) in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 29.11.2022 | - | NA | NA | Yes | CE/PLW/T-22/2022-23/PTA | M/s Gufraan Contractor and General order supplier, U.P | 1641754/- | 05.06.2023 | 20.01.2023 | - | Work in Progress
10 | CE/PLW/T-24/2022-23/PTA | Providing & Laying interlocking tiles from HMS level X-ing to bogie shop including footpath, rear side of LRS & LPG tank to PPS in workshop area, PLW/PTA. (2022-23) | Internet/ Manual | - | NA | 30.11.2022 | - | NA | NA | Yes | CE/PLW/T-24/2022-23/PTA | M/s S.K Builders, Patiala. | 5594445/- | 25.06.2023 | 02.01.2023 | - | Work in Progress
11 | CE/PLW/T-27/2022-23/PTA | Providing & Fixing of wooden flooring in badminton court in staff institution colony-II, PLW, Patiala. (2022-23) | Internet/ Manual | - | NA | 14.02.2023 | - | NA | NA | Yes | CE/PLW/T-27/2022-23/PTA | M/s Parquet Sports, Faridabad, India. | 879024/- | 15.07.2023 | 16.03.2023 | - | Work in Progress
12 | CE/PLW/T-29/2022-23/PTA | Operation, Repair and Maintenance of Sewage Treatment Plant in colony-II, PLW/Patiala for two years 2023-24 & 2024-25 | Internet/ Manual | - | NA | 22.03.2023 | - | NA | NA | Yes | CE/PLW/T-29/2022-23/PTA | M/s CHEM ECO Engineers | 2494800/- | 20.04.2023 | 19.04.2025 | - | Work in Progress

## Sheet 2
DETAILS OF WORKS AWARDED (WORKSHOP AREA & COLONY AREA)
S.N | Tender No. | Item / Nature of work | Mode of Tender Enquiry | Date of Publication of NIT | Type of Bidding (Single / Two Bid System) | Last date of receipt of tender | Nos. of tenders recd. | Nos. & names of parties qualified after technical evaluation. | Nos. & names of parties not qualified after technical evaluation | Whether contract awarded to lowest tenderer / Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract/ Original | Scheduled date of completion as per CA | LOA issue Date | Actual date of complete/extended | Reasons for delays if any
1 | CE/PLW/T-32/2024-25/PTA | Renovation and Alteration of SSE/Electrical Office in Colony-II area PLW, Patiala. | Internet/ Manual | - | NA | 29.11.2024 | - | NA | NA | Yes | CE/PLW/T-32/2024-25/PTA | M/s Kanwaljit Singh, Patiala. | 853418.62 | 02.04.2025 | 03.01.2025 | - | Work in Progress
2 | CE/PLW/T-33/2024-25/PTA | Construction of surface drain from Type-II qtrs to Lake in col-II PLW, Patiala. | Internet/ Manual | - | NA | 02.12.2024 | - | NA | NA | Yes | CE/PLW/T-33/2024-25/PTA | M/s Kamal Const. Co, Patiala. | 158971.76 | 09.05.2025 | 10.01.2025 | - | Work in Progress
4 | CE/PLW/T-34/2024-25/PTA | Extension of Bearing room (11m x 8m) and filling of pits, Hardonite flooring in old striping section and other allied works in Bogie shop in Work shop area, PLW/PTA. | Internet/ Manual | - | NA | 02.12.2025 | - | NA | NA | Yes | CE/PLW/T-34/2024-25/PTA | M/s S.K Builders, Patiala. | 6469180/- | 10.08.2025 | 11.12.2024 | - | Work in Progress
5 | CE/PLW/T-35/2024-25/PTA | Repair to Patroling road from scrap yard gate to W-shop main gate and repair to damaged periphery road in Work shop area, PLW Patiala. | Internet/ Manual | - | NA | 12.12.2024 |  | NA | NA | Yes | CE/PLW/T-35/2024-25/PTA | M/s Mittal Const. Co., Bathinda | 5499994/- | - | 26.12.2024 | - | Work Terminated
6 | CE/PLW/T-36/2024-25/PTA | Covered cabins for CDMS-DMS of store Depot Ph.-I in W-shop area PLW Patiala. | Internet/ Manual | - | NA | 12.12.2024 | - | NA | NA | Yes | CE/PLW/T-36/2024-25/PTA | M/s S.K Builders, Patiala. | 1491266/- | 18.03.2025 | 19.12.2024 | - | Work in Progress
7 | CE/PLW/T-37/2024-25/PTA | Providing of Flooring at steel yard phase-II with heavy duty interlocking tiles in workshop area, PLW Patiala. | Internet/ Manual | - | NA | 16.12.2024 | - | NA | NA | Yes | CE/PLW/T-37/2024-25/PTA | M/s S.K Builders, Patiala. | 4238266/- | 02.05.2025 | 03.01.2025 | - | Work in Progress
8 | CE/PLW/T-38/2024-25/PTA | Replacement to damaged Grill & Ventilator shutters of bath & toilet in Type-II(503 Nos.), III(260 Nos.) & IV qtrs in colony-II PLW Patiala | Internet/ Manual | - | NA | 16.12.2024 | - | NA | NA | Yes | CE/PLW/T-38/2024-25/PTA | M/s Mittal Const. Co., Bathinda | 8605239.57 | - | 26.12.2024 | - | Work Terminated
9 | CE/PLW/T-39/2024-25/PTA | Repair to Balance old damaged RCC Mumties by GC sheets in Type-II (53 stair cases) and Type -III (07 stair cases) Qtrs in colony-2, PLW/Patiala. | Internet/ Manual | - | NA | 18.12.2024 | - | NA | NA | Yes | CE/PLW/T-39/2024-25/PTA | M/s RPVL INFRA PVT. LTD., Gautam Budh Nagar, U.P | 2960652/- | 14.07.2025 | 15.01.2025 | - | Work in Progress
12 | CE/PLW/T-41/2024-25/PTA | Provision of tiles in bath, toilets and kitchen in balance type-2 quarter in colony-II area, PLW/Patiala. | Internet/ Manual | - | NA | 23.12.2024 | - | NA | NA | Yes | CE/PLW/T-41/2024-25/PTA | M/s Tarun Bansal Cont. Bathinda. | 21075962.56 | 14.09.2025 | 15.01.2025 | - | Work in Progress
13 | CE/PLW/T-42/2024-25/PTA | Replacement of rail of EOT crane track in zero bay of LMS in workshop area, PLW/Patiala. | Internet/ Manual | - | NA | 23.12.2024 | - | NA | NA | Yes | CE/PLW/T-42/2024-25/PTA | M/s Gupta Const. Bathinda. | 499616/- | 09.05.2025 | 10.01.2025 | - | Work in Progress
15 | CE/PLW/T-43/2024-25/PTA | Fencing in Type-V qtr (45 No.) in colony-I, PLW, Patiala. | Internet/ Manual | - | NA | 26.12.2024 | - | NA | NA | Yes | CE/PLW/T-43/2024-25/PTA | M/s Mittal Const. Co., Bathinda | 7864575/- | 09.07.2025 | 10.01.2025 | - | Work in Progress
17 | CE/PLW/T-44/2024-25/PTA | Repair to damaged SCI pipes in Type-2 double/triple storey qtrs. in colony-II area, PLW/Patiala. | Internet/ Manual | - | NA | 26.12.2024 | - | NA | NA | Yes | CE/PLW/T-44/2024-25/PTA | M/s DGS Infra Pvt. Ltd., Patiala. | 7760150/- | 24.09.2025 | 25.01.2025 | - | Work in Progress
18 | CE/PLW/T-45/2024-25/PTA | Housekeeping and Maintenance of camp office at Tilak Bridge New Delhi (for 24 Months), PLW/Patiala. | Internet/ Manual | - | NA | 15.01.2025 | - | NA | NA | Yes | CE/PLW/T-45/2024-25/PTA | M/s MAC Electro, Delhi | 3257518/- | 30.01.2027 | 31.01.2025 | - | Work in Progress
19 | CE/PLW/T-46/2024-25/PTA | Repair to internal roads of colony-I & II in PLW/Patiala. | Internet/ Manual | - | NA | 20.12.2024 | - | NA | NA | Yes | CE/PLW/T-46/2024-25/PTA | M/s DGS Infra Pvt. Ltd., Patiala. | 20993261/- | 11.05.2025 | 12.01.2025 | - | Work in Progress
18 | CE/PLW/T-47/2024-25/PTA | Replacement of damaged G.I Pipeline & Grid in colony-II PLW, Patiala. | Internet/ Manual | - | NA | 02.01.2025 | - | NA | NA | Yes | CE/PLW/T-47/2024-25/PTA | M/s FH Const., Amroha, Kanpur. | 2664484/- | 02.06.2025 | 03.02.2025 | - | Work in Progress
18 | CE/PLW/T-48/2024-25/PTA | Repair to damaged main road by providing CC interlocking tiles including chequered tiles in footpath from LAS to Gate B & Gate B to Gate A in workshop area, PLW, Patiala. | Internet/ Manual | - | NA | 20.01.2025 | - | NA | NA | Yes | CE/PLW/T-48/2024-25/PTA | M/s DGS Infra Pvt. Ltd., Patiala. | 9663326/- | 24.05.2025 | 25.01.2025 | - | Work in Progress